## Prerequisites
Component | Requirement | Notes
Azure Subscription | Active subscription with admin access | Verify permissions for network resource creation
AWS Account | Active account with admin access | Verify VPC and VPN creation permissions
Azure IP Range | 172.16.0.0/16 | For Azure Virtual Network
AWS IP Range | 10.0.0.0/16 | For AWS VPC
Azure Region | Select based on location | Choose region closest to your primary users
AWS Region | Select based on location | Should be relatively close to Azure region

## Azure Setup
Phase | Resource | Configuration | Estimated Time
1 | Resource Group | Name: RG-AzureAWSVPN | 5 minutes
1 | Virtual Network | Name: AzureVNet Address: 172.16.0.0/16 | 10 minutes
1 | Subnet | Name: Subnet-AzureVPN Address: 172.16.1.0/24 | 5 minutes
1 | Gateway Subnet | Address: /27 size from VNet space | 5 minutes
2 | VPN Gateway | Name: AzureVPNGateway SKU: VpnGw1 Type: Route-based | 45 minutes
3 | Local Network Gateway | Name: AWSLocalNetworkGateway IP: AWS VPN Public IP | 10 minutes
3 | VPN Connection | Name: AzureAWSVPNConnection Type: Site-to-site (IPsec) | 15 minutes

## AWS Setup
Phase | Resource | Configuration | Estimated Time
1 | VPC | Name: AWS-VPC Address: 10.0.0.0/16 | 10 minutes
1 | Subnet | Name: Subnet-AWSVPN Address: 10.0.1.0/24 | 5 minutes
2 | Virtual Private Gateway | Name: AWS-VPN-VGW | 10 minutes
2 | Customer Gateway | Name: Azure-CGW IP: Azure VPN Gateway Public IP | 10 minutes
3 | Site-to-Site VPN | Type: Static Routing: Static | 15 minutes
3 | Route Table | Add route for Azure subnet | 5 minutes

## Testing
Test Phase | Test Case | Expected Result | Status
Initial Connectivity | VPN Tunnel Status | Status should show as 'Connected' in both portals
Initial Connectivity | Route Propagation | Routes should appear in route tables
Network Testing | Deploy Test VM in Azure | VM should be created successfully
Network Testing | Deploy EC2 in AWS | EC2 instance should be created successfully
Network Testing | Ping Test Azure to AWS | Ping should succeed using private IPs
Network Testing | Ping Test AWS to Azure | Ping should succeed using private IPs

## Troubleshooting
Issue | Possible Cause | Resolution Steps
VPN Connection Not Established | Mismatched shared key | Verify shared key is identical on both sides
VPN Connection Not Established | Security group/NSG rules | Check ICMP and required ports are allowed
Cannot Ping Across VPN | Route tables not updated | Verify route propagation and static routes
High Latency | Region selection | Verify Azure and AWS regions are geographically close
Connection Drops | Dead Peer Detection (DPD) | Adjust DPD timeout values
BGP Not Working | ASN mismatch | Verify ASN numbers match on both sides